## Decisions
JSC-41B Decisions
Number | Decision | Day - Session | Notes
1 | The JSC decided to hold a focused workshop with partners on the science of climate intervention (geo-engineering). | D2-S4 | NOT DONE
2 | The JSC endorsed the community's agreement to support, in principle, the soft implementation to a new WCRP structure. This effectively means that the WCRP will move towards its new structure from 2021 onwards, as presented in the timeline at JSC41B. This also means that our research activities, in some cases, will operate within the new structure before all new Core Projects/Homes and Lighthouse Activities are fully designed and implemented. | CS
3 | The JSC decided that Core Projects/Homes and Lighthouse Activities must ensure diversity (gender, geopolitical etc.) in their planning and transition. Linked to ACTION 14. | D4-S7
4 | The JSC supported recommendations from the selection committee and will enter the negotiation phase with ESA to host the CMIP Project Office. ESA is option 1 and Ouranos is option 2. The agreement will be passed by the JSC before signing. | CS
5 | The JSC endorsed the 2021 draft WCRP budget | CS
6 | The JSC will work with the two new Homes, Earth System Modelling and Observational Capabilities and Regional (Climate) Information for Society, to develop a workshop for each
Acronyms
CP | Core Project
ESA | European Space Agency
JSC | Join Scientific Committee
JSC-41B | Extraordinary Session of the JSc held in November/December 2020
JSC-42 | 42nd Session of the JSC, June/July 2021
LHA | Lighthouse Activity
Model-Data Home | Earth System Modelling and Observational Capabilities Regional Climate Information for Societies Home
Regional-Info Home | Regional Climate Information for Societies Home
S2S | Subseasonal-to-Seasonal (S2S) Prediction Project
WMO | World Meteorological Organization

## Actions
JSC-41B Action Items
CS = Closed Session
Number | Action | Responsible | Category | Due Date | Day - Session | Priority (1 High - 3 low) | Complete | Notes
1 | GEWEX to share their white paper on the science direction and implementation needs for GEWEX for the next decade. | GEWEX Chairs and IPO | CP | Before GEWEX Scientific Steering Group Meeting | D1-S3 | 2 | Underway | Document almost finalised. Will be put on the GEWEX website replacing the older version of 2012 and also announced in e-news and newlsetter.
2 | Determine how best to tackle the issue of geoengineering/climate intervention, including: i) where it sits structurally in the new WCRP structure, and ii) developing a focused workshop with partners on the science of climate intervention | JSC Chairs, WCRP leadership | WCRP | 2021-03-01 | D2-S4 | 2 | No | Requires further discussion. Part of Safe Landing Climates?
3 | Investigate and report on how best to facilitate communication and collaboration throughout WCRP, between Homes, Lighthouse Activities and other WCRP elements towards a new Communication Plan (part of the Implementation Plan). | WCRP Secretariat (in consultation with community) | Comm | Conclusions in advance of JSC-42 | D2-S4 | 1 | Underway | Lack of staff resources to be able to make significant progress during last period, though some tools etc. have been looked into. Key topic for discussion at JSC42
4 | Determine how to incorporate Artificial Intelligence and Machine Learning practices more fully within WCRP and with partners | Digital Earths, Model-Data Home with WCRP Co-sponsors (in particular WMO) | WCRP | JSC-42 | D2-S5 | 2 | Underway | Strong linkages with WMO related activities.
5 | Determine mechanisms to connect local and regional scale activities to our global framing | JSC and regional consultation leads | Comm | JSC-42 | D2-S5 | 2 | Underway | Needs more consideration, but the Climate Research Forums are starting the dialogue needed to identify the best ways forward. It is envisioned that RIfS, once fully established, will have this as one of its objectives. Needs careful consideration in terms of clarity about goals and outcomes, given the need to prioritise with the tight funding environment. The discussion on future investment strategy in JSC42 is a good place to also consder this.
6 | Investigate mechanisms for engaging with partners that ensure that multiple conversations on similar topics are not occurring | WCRP leadership, Secretariat and international offices | Comm | JSC-42 | D3-S6 | 2 | No | There has been some discussions with partners in the LHAS, but this has been largely ad hoc. Should be considered during JSC42 as part of engagement & comms strategy (and perhaps under governance as well) on Day 4 - i.e. a protocol or register for key external engagemetns to keep all informed and avoid duplication. Also as part of the discussion during day 5.
7 | Explore whether a cross-cutting working group on tipping points and early warning systems has merit (bearing in mind activities of LHAs) | JSC and WCRP leadership | WCRP, LHA | JSC-42 | D3-S6 | 2 | No | This has not yet been discussed. There is progress in Safe Landing Climates LHA where they have established a subgroup on 'Tail risks, worst-case risk quantification' that includes tipping points. They also met with AIMES to discuss how to collaborate. Need to define what role can the WCRP play to advance this? Can also be a topic for the discussion of missing science break out on Day 4.
8 | Facilitate coordination between the Grand Challenges and Lighthouse Activities/Homes to map how the lessons learned and activities of the Grand Challenges can be taken forward into the other activities, where appropriate; discuss with Grand Challenge leads how they will sunset and contribute to the WCRP Open Science Conference. | WCRP Secretariat, Grand Challenge and Core Project leads etc. | GC | JSC-42 | D3-S6 | 1 | Underway | Interactions are underway with specifical meetings e.g. for GC Sea Level having been organised.
9 | Consider a 'lessons learned from the IPCC process' workshop after summer 2021 | JSC, WCRP leadership | Other | 2021-09-01 | D3-S6 | 3 | No | To be considered later in 2021. Consider planning a joint workshop.
10 | Provide advice and support to the WCRP Academy Lighthouse Activity on funding possibilities and structures | WCRP Secretariat | LHA | 2021-01-01 | D3-S6 | 2 | Underway | There was initial correspondence and advice was given and we continue to seek options (Narelle involved in Funding WG of the Academy). However, this will be ongoing as the LHA seeks to find long term funding.
11 | Finalize Core Project/Home reviews/plans | Core Project/Home Chairs | CP | JSC-42 | CS | 1 | Underway | To be finalised for JSC42
12 | Develop drafts of the LHA Science Plans, ensuring an adequate consultation process | Lighthouse Activity Chairs | LHA | JSC-42 | CS | 1 | Underway | To be finalised for JSC42
13 | Identify pilot or inception activities for the Lighthouse Activities | Lighthouse Activities | LHA | 2021-03-01 | D4-S7 | 2 | Underway | The LHAs have identified a number of potential activities. EPESC have advertised a workshop to take place in September 2021. We expect to see more planning in the second half of 2021 and early 2202.
14 | Develop a strategy to ensure that WCRP increases its geographical diversity, in the Lighthouse Activities and across the Programme | JSC | WCRP | Plan by JSC-42 |  |  | Underway | Increased emphasis on improving diversity in memberships (particaurly leadership) across WCRP. Also a focus of the Climate Research Forums.
15 | Streamline and expand WCRP Secretariat and international office support. This includes determining how best to provide long-term support (financial and human) to the WCRP Lighthouse Activities. | WCRP Head and JSC leadership | Support | Ongoing with report to JSC-42 | CS | 2 | Underway | Options are being discussed. Secretariat has appointed 3 new people, but also reduced in FTE over the years, including the likely loss of Mich with all his experience and "corporate knowledge" and relationships. Nonetheless, these 3 new positions will certainly tounaround the poor and uncertain situation we had through much of 2020. Have yet to progress the model for LHA Support Units, seeing their science / business plans and resource needs will assist with this next step. Income Strategy paper and associated discussions in JSC-42 will also asist..
16 | Establish two working groups on 1) governance and 2) budget and communications | JSC | BG, Comm | prior to JSC-42 | CS | 2 | Underway | Chairs and Head working on financial aspects. Next step is discussion at JSC-42 and then WG(s) will be established with a clear charge that builds on JSC discussions.
17 | Write a letter to the Extremes team explaining how to frame the Global Extremes Project proposal | JSC Chair and Vice-Chair, Lisa Alexander | WCRP | 2021-02-01 | CS | 1 | YES
18 | Determine a process for approving cross-cutting project proposals (including any office support) that makes the best use of opportunities without altering the high-level WCRP structure | JSC, WCRP Secretariat | BG | JSC-42 | CS | 2 | No | JSC Chairs have discussed this and it will be for discussion at JSC 42.
19 | Send a note to the JSC about the Seasonal to Subseasonal (S2S) membership proposal | WCRP Secretariat | WCRP | 2020-12-01 | CS | 2 | YES
20 | Work on a streamlined budget process, where a sub-group of the JSC works with the Core Projects to determine a pre-negotiated budget, perhaps with a mid-year review. | JSC, Head WCRP | BG | prior to JSC-42 | CS | 1 | No | General discussions held but not yet done.
21 | Send an annual communication to Nations explaining WCRP's use of previous contributions. | WCRP Secretariat | Comm | start process by Q1 2021 | CS | 2 | No | Part of financial reports.
22 | Develop an externally-focused high-level brochure about the new WCRP | WCRP Secretariat | Comm | 2021-02-01 | CS | 1 | Underway | A first draft was completed. Establishing a new brand identity for WCRP is now being explored and it was decided to complete this process first.
23 | Determine how to promote the Grand Challenge accomplishments: a series of products to celebrate the accomplishments (brochure, paper, video) of the Grand Challenges and other sunsetting activities | Grand Challenges, JSC WCRP Secretariat | GC | JSC-42 | CS | 2 | No | Lack of staff resources to be able to make significant progress during last period.
24 | Determine and report back on how to better involve the JSC in the 10NICS and also for the next WMO report and other similar cases | JSC Chair and Vice-Chair, Head WCRP | WCRP | 2021-03-01 | CS | 2 | Underway
Themes
Comm | Communications and Engagement
LHA | Lighthouse Activities
GC | Grand Challenges - transition plan
CP | Core Project internal reviews
BG | Budgeting and Governance
Support | Science support (Secretariat and IOs)
WCRP | WCRP Science
Other | Other